# Software Development Plan

TaskFlow AI - AI-Powered Task Management Platform

| Project Name | TaskFlow AI |
| --- | --- |
| Version | 1.0.0 |
| Date | December 24, 2024 |
| Target Competition | Microsoft Imagine Cup 2026 |

# 1. Project Overview

TaskFlow AI is an AI-powered task management web application that leverages Microsoft Azure AI services to provide intelligent task breakdown, progress visualization, and cross-device synchronization without requiring user accounts.

## 1.1 Project Objectives

- Provide AI-driven automatic task decomposition using Azure OpenAI Service

- Visualize task progress with percentage and graphical indicators

- Enable cross-device data synchronization without user registration

- Deliver web push notifications for task reminders

- Ensure responsive design for PC and mobile compatibility

## 1.2 Microsoft Imagine Cup Compliance

This project utilizes the following Microsoft AI services to meet the Imagine Cup requirement of at least 2 Microsoft AI services:

- Azure OpenAI Service: GPT-4o for intelligent task breakdown and natural language processing

- Azure AI Language: Text analytics for task categorization and sentiment analysis

- Azure Notification Hubs: Cross-platform push notification delivery

# 2. Development Timeline

| Date | Milestone | Deliverables |
| --- | --- | --- |
| Dec 24 | Development Start | Project setup, Azure resource provisioning |
| Dec 25-27 | Core Development | Backend API, AI integration, database setup |
| Dec 28-30 | Frontend Development | UI implementation, responsive design, notifications |
| Dec 31 | Integration Testing | End-to-end testing, bug fixes |
| Jan 1 | Production Deploy | Azure deployment, production release |
| Jan 2 | A/B Testing | User feedback collection, analytics setup |
| Jan 3 | Final Polish | Final improvements based on feedback |
| Jan 9 | MVP Submission | Imagine Cup MVP deadline |

# 3. Technology Stack

## 3.1 Frontend

- Framework: Next.js 14 with TypeScript

- Styling: Tailwind CSS

- State Management: Zustand

- Charts: Recharts for progress visualization

## 3.2 Backend

- Runtime: Node.js with Express.js

- Database: Azure Cosmos DB

- Authentication: Device-based UUID tokens

## 3.3 Azure Services

- Azure OpenAI Service: GPT-4o model for task AI

- Azure AI Language: Text analytics API

- Azure App Service: Web application hosting

- Azure Cosmos DB: NoSQL database for task storage

- Azure Notification Hubs: Push notification service

# 4. Development Phases

## Phase 1: Foundation (Dec 24-25)

- Azure resource group and service provisioning

- Project scaffolding with Next.js and Express

- Database schema design and Cosmos DB setup

- Basic API endpoint structure

## Phase 2: Core Features (Dec 26-28)

- Azure OpenAI integration for task breakdown

- Task CRUD operations

- Progress tracking and visualization

- Device synchronization mechanism

## Phase 3: Polish (Dec 29-31)

- Responsive UI implementation

- Push notification integration

- Performance optimization

- Comprehensive testing

# 5. Risk Management

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Azure API rate limits | High | Implement caching, request queuing |
| Tight timeline | High | MVP-focused scope, daily standups |
| Device sync conflicts | Medium | Last-write-wins with conflict detection |

# 6. Success Criteria

- All core features functional by Jan 1 production deployment

- At least 2 Microsoft AI services actively integrated

- Responsive design working on mobile and desktop

- Cross-device sync operational without user accounts

- Complete MVP submission materials by Jan 9